Mass Observation Archive strategic plan

2026-2031

Introduction & Timeframe

This five-year strategy will guide MOA from October 2026 to September 2031. It is structured around five key aims with multiple objectives delivering against one or more aim.

Although the strategy covers five years, MOA will produce annual plans to be shared with trustees each October. This annual planning will provide the flexibility to add new objectives, revise existing ones and drop those which are complete or no longer applicable.

Background & strategic context

This document was informed by discussions with the trustees, particularly at the meeting on 10 March 2026. It is written against a background of uncertainty and volatility in the higher education sector, with Sussex and other universities facing falling student numbers, a decline in research funding and severe financial challenges. As a significant part of MOA’s income is obtained from universities outside of the UK, it is also affected by strained geopolitical relationships and abrupt changes in US educational policy.

We are also alert to the opportunities and threats posed by emerging digital technologies, particularly generative AI. While these technologies are likely to develop rapidly over the next five years, and their impact is not yet fully understood, they should offer opportunities to improve and scale up the processing of the data MOA collects and provide enhanced search facilities to end users. Although LLM created content poses a potential threat in mimicking the human voice, this may also present an opportunity for MOA to affirm its position as an ‘authentically human’ repository for everyday thought and feeling in Britain.

Aims

MOA will pursue five broad aims, focused on making the charity a robust, dynamic and visible organisation serving multiple users and stakeholders.

- Digital innovation
We will responsibly harness technical innovations such as artificial intelligence to expand access, deepen research insight, and enhance participation in the collections of MOA while preserving ethical integrity, historical authenticity and contributor trust.

- Community management
We will strengthen the relationships between MOA and its stakeholders, from contributors and volunteers to regular researchers, to make it a more vibrant and sustainable organisation focused on its charitable objects.

- Audience development
We will expand the reach of MOA, to ensure that it represents ‘thought and feeling’ in modern Britain, is open to a broader demographic of Observers, and is used by a wider range of users.

- Financial sustainability
We will develop and secure regular income streams so that we can continue to invest in the staff that make MOA thrive.

- University of Sussex
We will build our presence at Sussex so that it is continually supported and cherished as a local asset by academics and students, without compromising its role as a national institution.

These aims are interlinked, and although objectives may be defined against a single aim they will often contribute to multiple aims. For example, 2.3 below clearly contributes to financial sustainability, even though it will be derived from wider work in community management.

Initial Objectives

Although objectives will be set at the start of each annual plan, these objectives have been identified at the outset of this strategy and mapped across the five years.

Aim 1: Digital innovation
We will responsibly harness technical innovations such as artificial intelligence to expand access, deepen research insight, and enhance participation in the collections of MOA while preserving ethical integrity, historical authenticity and contributor trust.

|  | Objective | Steps | Timeframe | Measure of success |
| --- | --- | --- | --- | --- |
| 1.1 | Ethical framework for AI | Develop a policy / guidelines for how MOA works with AI technologies and its expectations of stakeholders. It will acknowledge both the benefits and risks of these technologies and MOA’s duty of care for its contributors. Publish document on website. Review annually | Y1 Y1 Y2-5 | Delivery Delivery |
| 1.2 | Develop new platform(s) for providing access to data by researchers | Scope alternative to Box for sharing data Develop curated sets of data that can be used for teaching and outreach Explore funding opportunities for supporting data infrastructure | Y1 Y2-5 Y1 onwards | Delivery No of sets & users Delivery |
| 1.3 | Work with commercial and academic partners to explore new technologies | Continue testing Seeklight as a means of accelerating workflows Continue discussions with AM Digital on RAG and other services | Y1 onwards Y1 onwards | Updates in trustee reports Updates in trustee reports |

Aim 2: Community management
We will strengthen the relationships between MOA and its stakeholders, from contributors and volunteers to regular researchers, to make it a more vibrant and sustainable organisation focused on its charitable objects.

|  | Objective | Steps | Timeframe | Measure of success |
| --- | --- | --- | --- | --- |
| 2.1 | Develop and launch a new website that provides MOA with a more dynamic online presence | Engage developer to produce new website Implement new content scheduling plan Integrate website with research data platform (1.2) | Y1 Y2-5 Y2 | Delivery No of users Delivery |
| 2.2 | Grow e-newsletter | Develop editorial approach Maintain regular publication | Y1 Y1-5 | No of subscribers & engaged users |
| 2.3 | Increase awareness of MOA as a charity | Scope potential for individual giving, including legacies Scope revival of Friends scheme | Y1 Y1 | Donation income Delivery |

Aim 3: Audience development
We will expand the reach of MOA, to ensure that it represents ‘thought and feeling’ in modern Britain, is open to a broader demographic of Observers, and is used by a wider range of users.

|  | Objective | Steps | Timeframe | Measure of success |
| --- | --- | --- | --- | --- |
| 3.1 | 90th anniversary programme (Mass Observation Now?) | Showcase event at ACCA (May 2027) Regional programme of events Exhibition in The Gallery Online content programme focused on continuity and current relevance of MOA | Y1 Y1 Y1 Y1 | No of attendees No of cities and regions / No of attendees No of visitors / no of co-producers? No of users |
| 3.2 | Develop 12 May as vehicle for wider engagement | Evaluate impact of topic ‘nudges’ for each year Publish 12 May data as open access Expand use of open calls to target specific groups | Y1-2 Y2-3 Y2-3 | Delivery No of users No of contributors |
| 3.3 | Webinar programme | Continue webinar series Evaluate effectiveness of programme | Y1-2 Y3 | No of attendees Delivery |
| 3.4 | Guide to using Mass Observation | Produce and publish via Sussex Open Press, possibly co-produced with students | Y2-3 | Delivery |
| 3.5 | Work with community groups across UK to encourage day diary writing as a tool for engagement (Mass Observation X?) | Deliver training sessions and support to groups, focused on MO methods as framework for creative expression Create online resources supporting community groups | Y1-5 Y2-3 | No of training sessions No of users |

Aim 4: Financial sustainability
We will develop and secure regular income streams so that we can continue to invest in the staff that make MOA thrive.

|  | Objective | Steps | Timeframe | Measure of success |
| --- | --- | --- | --- | --- |
| 4.1 | Increase directive income through HE and third sector partnerships | Develop new partnerships | Y1-5 | Income earned |
| 4.2 | Encourage sponsorship of key MOA activities | Partner with organisations on open calls eg wildlife group supporting nature theme nudge for 12 May Seek funding from AM Digital to support academic conference attendance | Y1-5 Y1-5 | Income earned Income earned |
| 4.3 | Develop consultancy offer to community groups and charity partners (Mass Observation X?) | Define training offer and promote through 90th anniversary | Y1 | Income earned |
| 4.4 | License content to AM Digital | Confirm agreement for 2020-29 MOP | Y4 | Income earned |

Aim 5: University of Sussex
We will build our presence at Sussex so that it is continually supported and cherished as a local asset by academics and students, without compromising its role as a national institution.

|  | Objective | Steps | Timeframe | Measure of success |
| --- | --- | --- | --- | --- |
| 5.1 | Collaborate with School for Progressive Futures | Support elective programme with data and expertise Contribute to research and engagement programme as it emerges | Y1 Y1-5 | No of students Delivery |
| 5.2 | Contribute to teaching programmes at The Keep | Deliver taught collection-based sessions | Y1-5 | No of students |
| 5.3 | Support Sussex-led funding bids and initiatives | Continue Making & Using Social Archives Network meetings, supporting academics working with archives Continue conversations with Rachel Thomson around funding bid for infrastructure | Y1 Y1 | No of sessions Delivery |
| 5.4 | Support civic engagement programme | Respond to initiatives that may emerge from MOUs | Y1-5 | Delivery |

Governance and performance management

Once the strategy is agreed, KPIs will be defined as outputs or outcomes, with targets applied as appropriate on each annual plan. The success of these measures will inform the update reports provided to trustees as part of the standing meeting agenda.